## Sheet1
DLSU CCS Software Engineering
Activity RE3: Group Estimation
| Team Name: | SystemScape
| Teacher: | Ms. Ethel Ong
User Story |  |  | Team Member's Individual Estimate (Write the surname of the Members on the column.) | [9 empty] | Group Estimate | Assumptions
|  |  | Angeles | Coquilla | Cote | Fernandez | Poblete | Quindoza | Salceda | Tan | Uy | Velez
1 | A user (manager, technician) can login to view and manage the purchase order module, the inventory module, and the project assignment module. |  | 32 hours | 32 hours | 32 hours | 32 hours | 16 hours | 4 hours | 32 hours | 16 hours | 8 hours | 32 hours | 2 days | Database is designed and implemented in this stage
2 | A manager can export the data into spreadsheets to generate the reports. |  | 16 hours | 16 hours | 16 hours | 16 hours | 8 hours | 8 hours | 16 hours | 16 hours | 16 hours | 16 hours | 1 day | The database is designed efficiently enough to allow a simple query to produce this report
3 | A manager can view the list of suppliers to monitor the supplier details. |  | 4 hours | 8 hours | 8 hours | 8 hours | 4 hours | 8 hours | 8 hours | 4 hours | 8 hours | 8 hours | 8 hours | Extensive testing will be done to test data integrity
4 | A manager can filter the list of suppliers to allow faster discovery of a specific supplier. |  | 8 hours | 8 hours | 8 hours | 32 hours | 16 hours | 16 hours | 16 hours | 16 hours | 16 hours | 16 hours | 1 day | Algorithms will be used to account for human error in terms of misspellings
5 | A manager can record supplier details to have a directory of suppliers where the company could get their purchases as well as contact for any inquiries |  | 8 hours | 8 hours | 4 hours | 4 hours | 8 hours | 8 hours | 8 hours | 8 hours | 8 hours | 8 hours | 8 hours | UI design and testing for data integrity and for data duplication
6 | A manager can view a supplier to identify its attributes. |  | 2 hours | 2 hours | 2 hours | 2 hours | 4 hours | 4 hours | 4 hours | 2 hours | 4 hours | 4 hours | 4 hours | UI design, implementation, and testing will take up most of the time
7 | A manager can view the list of purchase orders to monitor the purchase order details. |  | 4 hours | 4 hours | 8 hours | 16 hours | 16 hours | 8 hours | 8 hours | 4 hours | 16 hours | 16 hours | 1 day | Extensive testing will be done to test data integrity
8 | A manager can filter the list of purchase orders to allow faster discovery of a specific purchase order. |  | 16 hours | 8 hours | 16 hours | 32 hours | 8 hours | 16 hours | 16 hours | 16 hours | 16 hours | 16 hours | 1 day | Algorithms will be used to account for human error in terms of misspellings
9 | A manager can create purchase orders so that s/he can monitor purchase transactions between the suppliers. |  | 8 hours | 8 hours | 8 hours | 4 hours | 8 hours | 8 hours | 8 hours | 8 hours | 8 hours | 8 hours | 8 hours | UI design and testing for data integrity and for data duplication
10 | A user (manager, technician) can view an item to identify its attributes. |  | 2 hours | 4 hours | 4 hours | 2 hours | 4 hours | 4 hours | 2 hours | 2 hours | 4 hours | 4 hours | 4 hours | UI design, implementation, and testing will take up most of the time
11 | A manager can update purchase orders to modify incorrect values and inconsistencies. |  | 4 hours | 8 hours | 4 hours | 4 hours | 8 hours | 16 hours | 4 hours | 4 hours | 8 hours | 8 hours | 8 hours | UI is similar to US#9
12 | A manager can record contract expiry dates so that he/she can monitor the expiry dates of equipment. |  | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | UI design and testing for data integrity and for data duplication
13 | A manager can view notifications on items with incoming contract expiry dates so that he/she can renew the contract in order to repair or to replace an equipment when complications arise. |  | 16 hours | 8 hours | 16 hours | 16 hours | 4 hours | 8 hours | 8 hours | 8 hours | 16 hours | 16 hours | 1 day | Observer Pattern will have to be implemented and tested extensively to ensure the manager receives the notifications
14 | A manager can record item warranty expiry dates so that he/she can monitor the warranty expiry dates of an item. |  | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4hours | 4 hours | 4 hours | UI design and testing for data integrity and for data duplication
15 | A manager can view notifications on items with incoming warranty expiry dates so that he/she can monitor the fee of maintaining the item which increases without the warranty |  | 4 hours | 4 hours | 8 hours | 8 hours | 4 hours | 4 hours | 4 hours | 4 hours | 8 hours | 8 hours | 8 hours | Similar to US#13
16 | A manager can view the list of employees to monitor the company staff. |  | 4 hours | 4 hours | 4 hours | 8 hours | 4 hours | 8 hours | 8 hours | 4 hours | 4 hours | 4 hours | 4 hours | Extensive testing will be done to test data integrity
17 | A manager can filter the list of employees to allow faster discovery of a specific employee |  | 8 hours | 8 hours | 16 hours | 16 hours | 8 hours | 16 hours | 16 hours | 16 hours | 16 hours | 16 hours | 1 day | Algorithms will be used to account for human error in terms of misspellings
18 | A manager can add employees to assign the items and the projects. |  | 4 hours | 8 hours | 8 hours | 4 hours | 8 hours | 8 hours | 8 hours | 8 hours | 8 hours | 8 hours | 8 hours | UI design and testing for data integrity and for data duplication
19 | A manager can view a specific employee entry to identify his/her employee attributes. |  | 2 hours | 4 hours | 4 hours | 2 hours | 4 hours | 4 hours | 4 hours | 2 hours | 4 hours | 4 hours | 4 hours | UI design, implementation, and testing will take up most of the time
20 | A manager can assign the items to an employee for a project to monitor the item’s availability and the projects and the employees handling the item |  | 8 hours | 16 hours | 4 hours | 8 hours | 8 hours | 8 hours | 4 hours | 8 hours | 8 hours | 16 hours | 1 day | Testing of the management of 3 tables will be extensive
21 | A user (manager, technician) can view the inventory to monitor purchases and its corresponding details. |  | 8 hours | 4 hours | 8 hours | 8 hours | 4 hours | 8 hours | 8 hours | 4 hours | 8 hours | 8 hours | 8 hours | Extensive testing will be done to test data integrity
22 | A user (manager, technician) can filter the inventory to allow faster discovery of a specific item. |  | 16 hours | 16 hours | 16 hours | 16 hours | 8 hours | 16 hours | 16 hours | 16 hours | 16 hours | 16 hours | 1 day | Algorithms will be used to account for human error in terms of misspellings
23 | A user (manager, technician) can add items to the inventory to record the receipt of ordered supplies from the suppliers. |  | 4 hours | 8 hours | 8 hours | 4 hours | 8 hours | 8 hours | 8 hours | 8 hours | 8 hours | 8 hours | 8 hours | UI design and testing for data integrity and for data duplication
24 | A user (manager, technician) can update the details of an item in the inventory to modify wrong details or to specify the status of an item. |  | 4 hours | 8 hours | 8 hours | 2 hours | 4 hours | 16 hours | 4 hours | 8 hours | 8 hours | 8 hours | 8 hours | Similar screen to US#23 is used
*Some team member estimates may not match with the submitted document.
**1 day = 16 hours