## Sheet1
Remove Assign Start and Assign End when the user chooses to set the status as "Unassigned" | Date Reported | Reported By | Description | Recommendation | Date Resolved | Resolved By | Description of Resolution
Version 3.3, Login | 2015-02-27 | Anton | The font used is tahoma | Change the font to arial | 2015-03-18 | Rissa | Set default font to Arial at login.java
Version 3.3, Login | 2015-02-27 | Anton | The JLabel lblLogIn and the JButton btnLogin contains wrong text | Replace "Log In" with "Sign In" | 2015-04-16 | Rissa | Changed the text | NOTES
Version 3.3, Login | 2015-02-27 | Anton | The text inside JTextField txtUsername and JPasswordField pwdPassword does not follow the UI design | Make the text more opaque and when the user clicks on the textbox, the text inside dissappears and the text returns if the user clicks outside of the textbox if the textbox remains empty |  |  | Design Changed. Labels beside textfield | Location of Issue | Can be identified in the following way:
Version 5.0, Add Supplier | 2015-03-08 | Clarisse | Question: Since currently an address is added by identifying the country, state and city, what will be the response of the UI if a country doesn't have states? | Remove the drop-down for the state if the identified country doesn't have states |  |  | Combobox is currently a textfield |  | If not all of the location details can be specified or not all are applicable, just try to be as specific as possible with it
Version 5.0, Add Supplier | 2015-03-08 | Clarisse | Question: What will be the response of the UI if, after identifying the city, the user changes the country or the state? | Set the drop-downs for state and city back to blank when the country is changed, and the city back to blank when the state is changed |  |  | Combobox is currently a textfield
Version 5.0, View Supplier, Inventory, Employee | 2015-03-08 | Mervin | The filter criteria panel does not close when the user clicks submit. | Make the filter criteria panel close when the user clicks submit. | 2015-04-16 | Rissa | Made the filter criteria panel close when the user clicks submit. | WHAT TO CHECK FOR
Version 5.0, View | 2015-03-12 | Anton | Click and drag any part of the gui will result in moving the whole gui | Make it only the top portion of the gui when click and drag it moves the gui not the whole gui | 2015-04-16 | Rissa | Made it only the top portion of the gui when click and drag it moves the gui not the whole gui | Compliance of code with the UI standards
Export Purchase Order Export Inventory | 2015-04-12 | Clarisse | Field "Name" is vague in the sense that it is not immediately obvious that it refers to the filename, and it is difficult to figure out whether to include the extension or not or even what the file extension is supposed to be | Change field name to "Filename" and display ".csv" beside the input field | 2015-04-16 | Rissa | Change field name to "Filename" and display ".csv" beside the input field | Consistency of the current UI with the user stories and specifications
Filter Supplier, Projects | 2015-04-15 | Mervin | There is no way to reset the filter. Once the modules are filtered, they stay filtered until the user logs out. | Add a remove filter feature. Edit(04-16-2015): While the fields in the filter are empty and the user submits the form, the original list(the one without filter) is the one displayed. | 2015-04-16 | Shayane | added a remove filter feature and informed the DEV team to add code statements for reverting the list to the orginal one if all blanks are empty | Competency of current UI given all possible test cases
Filter PO, Inventory, Employee | 2015-04-15 | Mervin | The "name" field of the filter is a drop down menu. It will be harder to filter the list once the list increases. | Instead of a drop down, use a free input from the user(e.g. textbox). | 2015-04-16 | Rissa | Made the drop downs autocomplete | Integration of current UI with model and controller
View specific PO | 2015-04-15 | Mervin | The user can edit the cells. | Disable the ability of the user to edit the cells. | 2015-04-16 | Shayane | Dsiabled cell isSelectable
Add Inventory Item Edit Inventory Item | 2015-04-15 | Clarisse | Even when the status is set to "Unassigned", the user is still able to select an employee as the "Assignee" | Disable the ability of the user to choose an assignee for unassigned items | 2015-04-16 | Gio | Successfully disabled "Assignee" once set to "Unassigned"
Edit Inventory Item (Software) | 2015-04-15 | Clarisse | The license key field displays the current date and time | Edit the license key field to display the current license key | 2015-04-16 | Gio | Successfully displayed License Key
Edit Supplier | 2015-04-16 | Clarisse | After modifying a supplier, the message displayed says "Supplier added successfully." | Change the message to "Supplier modified successfully." | 2015-04-16 | Rissa | Changed the message to "Supplier edited successfully."
Entire program | 2015-04-16 | Clarisse | There is no consistency in what pop-up messages do upon exit; when clicking "Ok" after when a message pops up after editing or adding an item, sometimes the user is returned to the view, and sometimes the user remains at the adding or editing part | Choose one of the two options and modify the parts of the program that are not consistent with it |  | Shayane
View Projects | 2015-04-16 | Clarisse | The start date and end date displayed include the time (which is always 00:00:00) | Only include the date | 2015-04-16 | Rissa | Only include the date
Edit Supplier | 2015-04-16 | Clarisse | The supplier's name is editable even though that is the primary key | Do not allow the user to edit the supplier name (otherwise find some way to properly modify the name without causing unexpected results, which is the job of the dev team, but this is a simpler solution) | 2015-04-16 | Rissa | Does not allow the user to edit the supplier name
Login | 2015-04-16 | Mervin | After logging out, "enter" key cannot be used to login unlike the first time the software is executed. | Make the login module consistent | 2015-04-16 | Rissa | Made the login module consistent
Inventory Module | 2015-04-16 | Mervin | The system does not display an item's status. The only probable indicator of whether an item is "in use" or "in store" is the fact that there is and there is not an assignee in another column, respectively. | Add a column called status. That's where the client can clearly tell apart whether an item is "in use" or "in store". | 2015-04-16 | Rissa | Status is either assigned or unassigned
Add Inventory Item Edit Inventory Item | 2015-04-17 | Clarisse | The user can choose "None" as an assignee even when the status is "Unassigned" | Do not include "None" as a choice in the drop-down list of assignees | 2015-04-19 | Gio | Removed "None" as a choice in the drop-down list of assignees
Add Inventory Item Edit Inventory Item | 2015-04-17 | Clarisse | Order of start and end dates in the form are inconsistent (i.e. Assign End comes before Assign Start, but Warranty Start and Contract Start come before Warranty End and Contract End) | Switch the places of Assign Start and Assign End | 2015-04-19 | Gio | Switched the places of Assign Start and Assign End
Add Inventory Item Edit Inventory Item | 2015-04-17 | Clarisse | When the status is set to "Unassigned", the drop-down for Assignee disappears, but Assign Start and Assign End do not | Remove Assign Start and Assign End when the user chooses to set the status as "Unassigned" | 2015-04-19 | Gio | Removed Assign Start and Assign End when the user chooses to set the status as "Unassigned"
Change Notification Settings | 2015-04-21 | Clarisse | When changing notification settings, the default is always set to 2 weeks even when the current settings aren't for 2 weeks | Display current notification settings when allowing the user to modify them
Edit Employee | 2015-04-21 | Clarisse | When submitting edited employee details, the success message displays "Employee added successfully." | Change the display to "Employee modified successfully."
Login | 2015-04-21 | Clarisse | Login fields do not clear after login, so when a user logs out, the old login details are still entered | Clear login fields upon successful login